## Sprint Planning & Backlog
Safal Events - Master Sprint Planning Sheet
User Story ID | User Story Name | Epic ID | Feature ID | Priority | Story Points | Target Platforms | User Role | Sprint Allocation | Status
US-01 | Multi-Role Authentication | EPIC-01 | FEAT-01 | Critical | 5 | Web/Mobile | All Roles | Sprint 1 | Completed
US-02 | Staff Scope Gating | EPIC-01 | FEAT-02 | High | 3 | Mobile | Staff | Sprint 1 | Completed
US-03 | Host Event Creation | EPIC-02 | FEAT-03 | Critical | 8 | Web/Mobile | Host | Sprint 1 | Completed
US-04 | Host Ticket & RSVP Builder | EPIC-02 | FEAT-04 | High | 5 | Web/Mobile | Host | Sprint 2 | Completed
US-05 | Host Waitlist Settings | EPIC-02 | FEAT-05 | Medium | 5 | Web/Mobile | Host | Sprint 2 | Completed
US-06 | Host Check-In Config | EPIC-02 | FEAT-06 | Medium | 3 | Web/Mobile | Host | Sprint 2 | Completed
US-07 | Host Co-Host Collaboration | EPIC-02 | FEAT-07 | Medium | 5 | Web | Host | Sprint 3 | Backlog
US-08 | Host Shared Photo Gallery | EPIC-03 | FEAT-08 | Low | 5 | Web/Mobile | Host | Sprint 3 | Completed
US-09 | Host Message Automation Rules | EPIC-04 | FEAT-09 | Medium | 8 | Web | Host | Sprint 4 | Backlog
US-10 | Host Security Audit Trail Logs | EPIC-04 | FEAT-10 | Low | 5 | Web/Mobile | Host | Sprint 4 | Backlog
US-11 | Host Integrated Services | EPIC-04 | FEAT-11 | Low | 5 | Web/Mobile | Host | Sprint 4 | Backlog
US-12 | Guest Event Browse & Search | EPIC-05 | FEAT-12 | Medium | 5 | Web/Mobile | Guest | Sprint 1 | Completed
US-13 | Guest RSVP Submission | EPIC-05 | FEAT-13 | Critical | 5 | Web/Mobile | Guest | Sprint 1 | Completed
US-14 | Guest Payment & Checkout | EPIC-05 | FEAT-14 | Critical | 8 | Web/Mobile | Guest | Sprint 2 | Completed
US-15 | Guest Ticket Pass Wallet | EPIC-05 | FEAT-14 | Critical | 5 | Web/Mobile | Guest | Sprint 1 | Completed
US-16 | Guest Host Messaging Inbox | EPIC-05 | FEAT-15 | Medium | 5 | Web/Mobile | Guest | Sprint 3 | Completed
US-17 | Staff Gate Scan Verification | EPIC-06 | FEAT-16 | Critical | 8 | Mobile | Staff | Sprint 1 | Completed
US-18 | Staff Partial Party Check-in | EPIC-06 | FEAT-17 | High | 5 | Web/Mobile | Staff | Sprint 2 | Completed
US-19 | Staff Walk-in Guest Management | EPIC-06 | FEAT-18 | High | 5 | Web/Mobile | Staff | Sprint 2 | Completed
US-20 | Superadmin Host Compliance Review | EPIC-07 | FEAT-19 | High | 5 | Web | Superadmin | Sprint 1 | Completed
US-21 | Superadmin Hosts & Events Control | EPIC-07 | FEAT-20 | Medium | 5 | Web | Superadmin | Sprint 3 | Backlog
US-22 | Superadmin System Customization | EPIC-07 | FEAT-20 | Medium | 5 | Web | Superadmin | Sprint 4 | Backlog
US-23 | Host Event Dress Code Config | EPIC-02 | FEAT-20 | Medium | 5 | Web/Mobile | Host | Sprint 1 | Completed
US-24 | Event Mode & Venue Details Config | EPIC-02 | FEAT-21 | Critical | 8 | Web/Mobile | Host | Sprint 1 | Completed