## Sprint Plan
Epic ID | Epic Description | Feature ID | Feature Description | User Story ID | User Story Description | Priority | Developer Assigned | Sprint | Timeline | Mockup URL
NAV | App Shell, Navigation & Platform | FEAT-NAV-01 | Splash & role-based navigation | US-NAV-001 | As a user opening the app, I want to see a branded splash that then takes me into the right place, so that the app starts fast and lands me correctly. | High | Developer 1 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
NAV | App Shell, Navigation & Platform | FEAT-NAV-01 | Splash & role-based navigation | US-NAV-002 | As a user, I want to navigate via bottom tabs appropriate to my context, so that I can move around the app easily. | High | Developer 1 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
NAV | App Shell, Navigation & Platform | FEAT-NAV-02 | Phone-frame, theming & live store | US-NAV-003 | As a reviewer on a browser, I want to the app to look like a handset when opened on the web, so that I can preview the mobile UI without a device. | Medium | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
NAV | App Shell, Navigation & Platform | FEAT-NAV-02 | Phone-frame, theming & live store | US-NAV-004 | As a user, I want to a consistent, branded look across screens, so that the app feels polished and easy to use. | Medium | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
NAV | App Shell, Navigation & Platform | FEAT-NAV-02 | Phone-frame, theming & live store | US-NAV-005 | As a user, I want to actions like check-in to reflect immediately across screens, so that the prototype behaves like a connected app. | Medium | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-01 | Guest Mode browse & discovery | US-BROWSE-001 | As a newly installed user, I want to explore the app without logging in or registering, so that I get a feel for it before committing. | High | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-01 | Guest Mode browse & discovery | US-BROWSE-002 | As a guest-mode user, I want to a landing screen that showcases events and categories, so that I quickly see what's on. | Medium | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-01 | Guest Mode browse & discovery | US-BROWSE-003 | As a guest-mode user, I want to browse and search the full event list, so that I can find something specific. | Medium | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-01 | Guest Mode browse & discovery | US-BROWSE-004 | As a guest-mode user, I want to see full event details before deciding, so that I have what I need to decide. | High | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-01 | Guest Mode browse & discovery | US-BROWSE-009 | As a platform owner, I want to no data to be written until the user authenticates, so that guest browsing is safe and side-effect free. | Medium | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-02 | Persistent entry & gated auth | US-BROWSE-005 | As a guest-mode user, I want to an always-visible way to sign in, so that I can create an account whenever I'm ready. | Medium | Developer 4 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-02 | Persistent entry & gated auth | US-BROWSE-006 | As a guest-mode user, I want to to be sent to Login/Register only when an action needs an account, so that I'm never blocked until necessary. | High | Developer 4 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-03 | Return-to-intent, cancel & sessions | US-BROWSE-007 | As a guest-mode user, I want to to be returned to the exact action I tapped after signing in, so that the flow feels seamless. | High | Developer 1 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-03 | Return-to-intent, cancel & sessions | US-BROWSE-008 | As a guest-mode user, I want to to dismiss the auth screen and keep browsing, so that I'm never trapped in a login wall. | Medium | Developer 1 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BROWSE | Guest Mode — Browse before login | FEAT-BROWSE-03 | Return-to-intent, cancel & sessions | US-BROWSE-010 | As a returning or linked user, I want to to skip Guest Mode when remembered, and have links respect gating, so that returning and shared-link journeys are smooth. | Low | Developer 1 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-01 | Signup (Guest/Host, Individual & Organization) + OTP | US-AUTH-001 | As a new user, I want to clearly choose to register as a Guest or a Host, so that I land in the right experience. | High | Developer 2 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-01 | Signup (Guest/Host, Individual & Organization) + OTP | US-AUTH-002 | As a individual host, I want to register with my name and email/phone, so that I can create and manage my own events. | High | Developer 2 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-01 | Signup (Guest/Host, Individual & Organization) + OTP | US-AUTH-003 | As a organization representative, I want to register my organization with its details and documents, so that my org can host under a verified profile. | High | Developer 2 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-01 | Signup (Guest/Host, Individual & Organization) + OTP | US-AUTH-004 | As a registering user, I want to confirm my email/phone with a one-time code, so that only verified people create accounts. | High | Developer 2 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-02 | Login, staff invite login & session | US-AUTH-005 | As a registered Guest or Host, I want to log in with email/phone and reach the right flow, so that one login does the right thing. | High | Developer 3 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-02 | Login, staff invite login & session | US-AUTH-006 | As a invited staff member, I want to sign in with my Invite ID and email/phone, so that I reach my assigned event with only my role's screens. | High | Developer 3 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AUTH | Authentication, Signup & Login | FEAT-AUTH-02 | Login, staff invite login & session | US-AUTH-007 | As a signed-in user, I want to sign out or switch to another account, so that I can change context on a shared device. | Medium | Developer 3 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-01 | RSVP flow & tickets/QR pass | US-GUEST-001 | As a guest, I want to RSVP through a guided flow, so that I can register for an event. | High | Developer 4 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-01 | RSVP flow & tickets/QR pass | US-GUEST-002 | As a guest, I want to clear status for each of my RSVPs, so that I know exactly where I stand. | High | Developer 4 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-01 | RSVP flow & tickets/QR pass | US-GUEST-003 | As a guest, I want to open my QR pass for a confirmed event, so that I can be checked in at the gate. | High | Developer 4 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-01 | RSVP flow & tickets/QR pass | US-GUEST-004 | As a guest, I want to see all my RSVPs in one place, so that I can track what I'm attending. | High | Developer 4 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-02 | Guest messaging & profile | US-GUEST-005 | As a guest, I want to message the host for an event that allows it, so that I can ask questions. | Medium | Developer 1 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-02 | Guest messaging & profile | US-GUEST-006 | As a guest, I want to see my conversations and delivery logs, so that I keep track of communications. | Low | Developer 1 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
GUEST | Guest — RSVP, Tickets & Messaging | FEAT-GUEST-02 | Guest messaging & profile | US-GUEST-007 | As a guest, I want to see my profile and notification preferences, so that I control my experience. | Low | Developer 1 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
HOST | Host Tools | FEAT-HOST-01 | Host dashboard & events list | US-HOST-001 | As a host, I want to an overview of my events and activity, so that I stay on top of things. | High | Developer 2 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
HOST | Host Tools | FEAT-HOST-01 | Host dashboard & events list | US-HOST-002 | As a host, I want to see and open my events, so that I can manage each one. | High | Developer 2 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
HOST | Host Tools | FEAT-HOST-02 | Create & manage events | US-HOST-003 | As a host, I want to create an event with its key settings, so that I can launch a new event. | High | Developer 3 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
HOST | Host Tools | FEAT-HOST-02 | Create & manage events | US-HOST-004 | As a host, I want to a tabbed hub to manage one event, so that everything for an event is in one place. | High | Developer 3 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
HOST | Host Tools | FEAT-HOST-02 | Create & manage events | US-HOST-005 | As a host, I want to edit an event's settings on mobile, so that I can adjust an event on the go. | Medium | Developer 3 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
HOST | Host Tools | FEAT-HOST-03 | Host account | US-HOST-006 | As a host, I want to manage my account, earnings and settings, so that I control my host profile. | Low | Developer 4 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
APPROVAL | Approval & Waitlist (Mobile) | FEAT-APPROVAL-01 | Approval queue & waitlist | US-APPROVAL-001 | As a host or permitted staff, I want to approve or reject pending RSVPs, so that I curate who attends. | High | Developer 1 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
APPROVAL | Approval & Waitlist (Mobile) | FEAT-APPROVAL-01 | Approval queue & waitlist | US-APPROVAL-002 | As a host, I want to capacity-full RSVPs to wait for my approval, so that I decide who gets a freed seat. | High | Developer 1 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
APPROVAL | Approval & Waitlist (Mobile) | FEAT-APPROVAL-02 | Status badges & live reflection | US-APPROVAL-003 | As a guest, I want to see my approval state on my tickets and the event, so that there's no ambiguity. | Medium | Developer 2 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
APPROVAL | Approval & Waitlist (Mobile) | FEAT-APPROVAL-02 | Status badges & live reflection | US-APPROVAL-004 | As a host, I want to approvals and check-ins to update my dashboard immediately, so that I see accurate numbers in real time. | Medium | Developer 2 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
STAFF | Staff, Roles & QR Check-in | FEAT-STAFF-01 | Staff login & permission gating | US-STAFF-001 | As a staff member, I want to sign in via Invite ID and see only my permitted screens, so that I do my job with the right access. | High | Developer 3 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
STAFF | Staff, Roles & QR Check-in | FEAT-STAFF-01 | Staff login & permission gating | US-STAFF-005 | As a staff member, I want to to be shown only what my role allows, so that I cannot access unauthorized functions. | High | Developer 3 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
STAFF | Staff, Roles & QR Check-in | FEAT-STAFF-02 | QR gate check-in | US-STAFF-002 | As a gate staff, I want to scan a guest's pass and validate it, so that only valid, approved guests are admitted. | High | Developer 4 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
STAFF | Staff, Roles & QR Check-in | FEAT-STAFF-02 | QR gate check-in | US-STAFF-003 | As a gate staff, I want to check a guest in and have it propagate, so that attendance is tracked accurately. | High | Developer 4 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
STAFF | Staff, Roles & QR Check-in | FEAT-STAFF-03 | Staff & roles management | US-STAFF-004 | As a host, I want to invite staff and define roles on mobile, so that I can run my team from my phone. | Medium | Developer 1 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
MSG | Per-Event Messaging | FEAT-MSG-01 | Per-event messaging config & threads | US-MSG-001 | As a host, I want to toggle guest messaging per event, so that I control messaging per event. | Medium | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
MSG | Per-Event Messaging | FEAT-MSG-01 | Per-event messaging config & threads | US-MSG-002 | As a guest, I want to see Message host only when allowed, so that messaging matches the host's setup. | Medium | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
MSG | Per-Event Messaging | FEAT-MSG-01 | Per-event messaging config & threads | US-MSG-003 | As a staff member, I want to read/reply to messages only if permitted, so that access matches my role. | Low | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PLAT | Cross-cutting & Delivery | FEAT-PLAT-01 | Aligned layout & web build | US-PLAT-001 | As a any user, I want to screens that are aligned and easy to use, so that the app feels professional. | High | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PLAT | Cross-cutting & Delivery | FEAT-PLAT-01 | Aligned layout & web build | US-PLAT-002 | As a reviewer, I want to the app to run on the web inside a phone frame, so that I can preview it in a browser. | Medium | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PLAT | Cross-cutting & Delivery | FEAT-PLAT-02 | Deployment, persistence & prototype data | US-PLAT-003 | As a product owner, I want to to host the web build for sharing, so that stakeholders can try it via a link. | Low | Developer 4 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PLAT | Cross-cutting & Delivery | FEAT-PLAT-02 | Deployment, persistence & prototype data | US-PLAT-004 | As a returning user, I want to my session remembered across visits (web), so that I skip re-logging in. | Low | Developer 4 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PLAT | Cross-cutting & Delivery | FEAT-PLAT-02 | Deployment, persistence & prototype data | US-PLAT-005 | As a platform owner, I want to the app to run without a backend, so that the prototype is self-contained. | Medium | Developer 4 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
UIPRICE | Pricing, Subscription & Billing UI | FEAT-UI-02 | Host billing & subscription dashboard | US-UI-002 | As a host, I want to see my plan, usage and upgrade options, so that I understand my limits and how to upgrade. | High | Developer 1 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
UIPRICE | Pricing, Subscription & Billing UI | FEAT-UI-04 | Photo upload permission alignment | US-UI-004 | As a host, I want photo permissions grouped clearly in event settings and pricing, so that I understand and control photo features. | Medium | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-01 | Configure age restriction | US-EVENT-013 | As a host, I want to toggle an age restriction and set a minimum age, so that only eligible guests attend. | High | Developer 1 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-02 | DOB collection at RSVP | US-EVENT-014 | As a guest RSVPing to an age-restricted event, I want to enter my date of birth, so that the platform verifies I meet the age requirement. | High | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-03 | Additional guest name + DOB | US-EVENT-015 | As a guest adding extra guests, I want to enter each guest's details, so that the host has a complete, age-compliant manifest. | High | Developer 1 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-04 | Host view of guest ages | US-EVENT-016 | As a host, I want to see ages and party members of my guests, so that I can verify compliance at the door. | Medium | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-05 | QR pass & check-in age verification | US-EVENT-017 | As gate staff, I want an at-a-glance age indicator, so that I can approve entry quickly. | Medium | Developer 1 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PHOTO | Event Photo Album | FEAT-PHOTO-01 | Enable & configure album | US-PHOTO-001 | As a host, I want to enable a shared photo album with upload permissions, so that guests can relive the event. | High | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PHOTO | Event Photo Album | FEAT-PHOTO-02 | Host album management & moderation | US-PHOTO-002 | As a host, I want to manage album photos, so that I keep content appropriate. | High | Developer 1 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
PHOTO | Event Photo Album | FEAT-PHOTO-03 | Guest view & upload | US-PHOTO-003 | As a guest, I want to view and (when allowed) add photos, so that I can share my perspective. | Medium | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
BRAND | Platform Consistency & Branding | FEAT-BRAND-03 | Updated logo lockup | US-PLAT-003 | As a user, I want the new logo presented well, so that branding is clear. | Low | Developer 1 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile

## Sprint Summary
Sprint | Timeline | Epics in sprint | # Features | # User Stories
S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | App Shell, Navigation & Platform (NAV), Cross-cutting & Delivery (PLAT) | 4 | 10
S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Guest Mode — Browse before login (BROWSE) | 3 | 10
S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Authentication, Signup & Login (AUTH) | 2 | 7
S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Guest — RSVP, Tickets & Messaging (GUEST), Per-Event Messaging (MSG) | 3 | 10
S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Host Tools (HOST), Approval & Waitlist (Mobile) (APPROVAL) | 5 | 10
S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Staff, Roles & QR Check-in (STAFF) | 3 | 5

## Read me
SafalEvents Mobile — Sprint Planning
Product
SafalEvents mobile app (Expo / React Native) — host, guest & staff, with a phone-frame web build.
App / preview URL
Mobile app (Expo) — https://github.com/Tirth11/Safalevents_Mobile
(Replace the Mockup URL with your Netlify web-preview URL once the web build is deployed.)
How to use
Sheet 'Sprint Plan' = one row per user story, grouped Epic -> Feature -> User Story.
Sheet 'Sprint Summary' = sprint timeline overview.
Use the header filters to slice by Epic, Sprint, Priority or Developer.
Notes
'Developer Assigned' values are placeholders (round-robin) — replace with your team.
Sprints are 2 weeks; the schedule starts 22 Jun 2026 and is a suggested sequence by dependency.
Story/epic content is the single source of truth shared with SafalEvents_Mobile_User_Stories.docx.